## Title Page
Western Australian Electricity Market
Build Pack
List of Market Gateway Defects
|  | Client | Metering Services
|  | Project Name | WAEM Build Pack
|  | Document Number | 5364662 (Published Version)
|  | Document Title | List of Market Gateway Defects
|  | Revision Status | 1.5
Document prepared by:
Western Power
ABN 18540492861
|  | Prepared by: Metering Services | Reviewed by OR Approved by::
|  | Name (prepared by) | Name (reviewed/approved by)
|  | WAEM Build Pack Working Group | Metering Services Manager
Document history
Version | Date | Changes
1.0 | 2008-09-30 | Initial version
1.1 | 2009-02-06 | Added Issue 64: Single quotes in WA aseXML Added Issue 65: ">: not handled by XML correctly
1.2 | 2012-09-07 | Added Issue 66: Invalid NEM12 Files - NMIConfiguration Sent to Market Added Issue 67: Invalid NEM12 Files During Meter Exchange - Duplicate 200 and 300 Records Sent to Market
1.3 | 2015-10-23 | Added new column to capture resolution details of Defects. Added Issues 68 to 72. Closed Issues 5, 9, 13, 14, 15, 32, 37, 41, 43, 66
1.4 | 2016-10-19 | Added Issue 73
1.5 | 2016-11-04 | Added Issue 74

## Defect List
Resolution | Status | Item# | Procedure/Document | Process | Description | Date Created | Last Updated | Status | Change Priority | Proposed Resolution Date | Mitigation Proposal
| Open | 1 | Customer and Site Details Details | Applicable Events | Where WP is rejecting Site Access arrangements, the following reject details are correct except for the Context. This should be left blank if no specific field in the request has caused the issue. In this instance all fields in the request contribute to the reject (i.e. all data provided is already set correctly, so no change is required), so Context should be blank. - <TransactionAcknowledgement initiatingTransactionID="BS_20080610115009125" receiptID="WPNTWRKS-3111a-22652878" receiptDate="2008-06-10T12:28:46+08:00" status="Reject" duplicate="No" acceptedCount="0"> - <Event severity="Error" class="Application"> <Code>202</Code> <KeyInfo>8002033147</KeyInfo> <Context>No MBS change required</Context> <Explanation>No MBS change required</Explanation> </Event> </TransactionAcknowledgement> | 2008-06-10 |  | Open | Low |  | Ignore context info on Site Access TransAcks
| Open | 2 | Customer Transfer | Withdrawn CTR | Following the acceptance of a Withdrawn CTR, the Network Operator should be sending a Notification with a status of 'CAN' to both the related Retailers (current and incoming). Only one notification is being sent to the current Retailer. No notification is sent to the incoming retailer. | 2008-05-20 |  | Open | Low |  | The participant missing a notification is the party that has requested the Cancellation. A TransAck will be sent to this participant notifying them of the acceptance on the Cancel. The receipt of this transaction will confirm that the request to cancel the service order has been completed.
| Open | 3 | Customer Transfer | Invalid Customer Transfer Process | If a CTR is already in progress and a second CTR is submitted, WP will send a TransNack (Reject) with reason of "Transfer already in progress". This process also sends a CTR Notification to the Requestor with a status of "REJ" and the same reason of "Transfer already in progress". The Notification should not be sent in this scenario. The TransNack should close the process. | 2008-05-20 |  | Open | Low |  | Ignore the Notification with status of "REJ". This is only intended for the Metering Service Centre (Web Portal) to facilitate the update of the Web displayed CTR status, and should not be sent as an XML message to a Retailer.
n/a | Closed | 4 | Meter Data Process | Meter Data Verify | Upon completion, an MDV should send readings to the requestor if the readings have been "Replaced". The immediate MDN is not being published and the readings are only published in the next full MDN. | 2008-05-20 |  | Cancelled | Medium |  | Expanded defect 5 to cover this issue.
Delivered in CR#9 on 30/04/2012 | Closed | 5 | Meter Data Process | Meter Data Verify | InitiatingTransactionID: The MDV TransactionID should be included in the related MDN for replaced readings in the InitiatingTransactionID field. This relates the readings in the MDN to the MDV that initiated the change in the re-readings. This MDV TransactionID is not currently published in this way in the MDN. Eroneous 500/550 in MDV related MDN's: Historically there was an issue with the MDN including a 500/550 record in the MDN response for an MDV. The MDN should not include a 500/550 record that refers to the MDV TransactionID. NB: Although the TransactionID can be up to 36 characters, there is a 15 character limit on the RetailerReference in the 500/550 record. This should only used for Service Orders, and an MDV is a Meter Data Process and not a service order. No MDN published for MDV's completed with "Replace": The Network Operator system is not currently publishing a specific MDN with the replaced readings that relate to the processing of an MDV. The changed readings are only published in the next full MDN to the participant. | 2008-05-20 | 2008-08-20 | Open | Medium |  | InitiatingTransactionID: For a completed MDV, wait for the next standard MDN reading file to be delivered before processing the MDV response. This will not have a 550 record. Erroneous 500/550 in MDV related MDN's: Code participants are advised to raise the MDV with a 15 character TransactionID or to strip out the RetailerReference from the NEM12/NEM13 record on receipt of the MDN if it causes problems in downstream applications. No MDN published for MDV's completed with "Replace": For a completed MDV, wait for the next standard MDN reading file to be delivered before processing the MDV response. There will not be a small MDN related to the MDV readings only.
| Closed | 6 | Meter Data Process | Meter Data Verify | The MDV MDN should include an initiating transactionid of the original MDV request. The requirement is also explained in the "Participant build Pack Section 1.8.3d" NB: The Meter Data History does send a related MDN which has the initiating transactionid. | 2008-05-20 | 2008-08-05 | Cancelled | Medium |  | Expanded defect 5 to cover this issue.
| Open | 7 | Meter Data Process | Meter Data Notify - NEM12 | This as a business process issue: WP does not collect the register reads for manually read interval Meters (MRIM). As per section 3.3.4 of the "Meter Data File Format Specification NEM12 & NEM13", the Network Operator must provide the market with "Index reads for Type 5 Interval Meters". Western Power does not currently meet this obligation. | 2008-05-20 |  | Open | Low |  | None identified.
| Open | 8 | Meter Data Process | Meter Data Notify - NEM13 | For customers on Self read cards, if we create a substitute readings when the card has not been returned, the substitution reason code is being published as "meter not in HH" instead of "customer Read not supplied" (WP Ref 3883). | 2008-05-20 | 2008-08-25 | Open | High | End of October 2008 | Readings for customers on Self read cards may be sent to the participant with the wrong substitution code. Use own records or the Standing Data Read Type to confirm that the substitution is for an Self read customer.
Resolved via business process. | Closed | 9 | Meter Data Process | Meter Data Notify - NEM13 | Reason codes incorrect: The meter reader input skip code 28 - Wet Paint, but we are publishing an est/subst reason code of "Wrong Tariff" (WP Ref 3918). | 2008-05-20 | 2008-08-25 | Fix in Test |  | End of October 2008 | Resolved via procedure implementation. Meter Readers have a valid set of skip codes provided on the WP skip meter cards to select from. Skip Code 28 is not listed on the card as a valid option. In AEMO's 2014 Meter Data File Format Spec NEM12 & NEM13 document, both Wet Paint (49) and Wrong Tariff (50) are obselte codes, that are only to be used when providing historical data.
| Open | 10 | Meter Data Process | Meter Data Verify | B2B Procedures Clause 2.6.i (pg 16) – states that if an MDP is resending an MDN due to a “reject” or “partial” the MDN resent must have the same Request ID as the original MDN. This has not been done in the WA market. | 2008-05-28 |  | Needs testing! | Low |  | The priority for this change will need to be determined by the market participants. At this stage WP expect a low need for this process, especially given the MDN can not be TransNack'd on the content of the reading. Those issues should be raised by MDV's.
| Open | 11 | Meter Data Process | Retailer Readings | In the WA Metering Code clause 5.16 states “If a user collects or receives energy data from a metering installation then the user must provide the network operator with the energy data (in accordance with the communication rules) within 2 business days after collecting or receiving the energy data (or such other time as is specified in the applicable service level agreement)” The WA Market interfaces do not support this market requirement and Synergy do have franchise reading data that they are required to provide to Western Power. | 2008-06-10 |  | Open | Low |  | Off-market communication processes are under review and discussion.
| Open | 12 | Meter Data Process | Meter Data Verify | Section 2.6e 1: The NEM In the WA B2B Procedure Meter Data Process - Section 2.10.1 has an MDV Investigation code of “Recipient not responsible for the NMI”, however, WP does not accept an MDV with this investigation code. WP systems must be changed to allow this. | 2008-06-10 | 2008-07-19 | Open | Low |  | Please use a code of "Other" and include an investigation description of "recipient not responsible for NMI”.
Delivered in CR#9 Part 2 on 24/12/2012 | Closed | 13 | Service Orders | Applicable Events | Section 4.4.1 : According to the Build Pack, if a reschedule is required for a Service Order (1912), this should be issued with: 1) Severity = "Warning" 2) Keyinfo = ServiceOrderNumber (eg ALBC_109985_1 from the Service Order request) 3) Context = ScheduledDate (eg 2008-06-10 from the Service Order request) 4) Leave explanation line as currently published Instead we currently issue the following: - <TransactionAcknowledgement initiatingTransactionID="CIS_20080610_ALBC_109985_1" receiptID="WPNTWRKS-3111a-22661449" receiptDate="2008-06-10T14:23:22+08:00" status="Accept" duplicate="No" acceptedCount="1"> - <Event severity="Error" class="Application"> <Code>1912</Code> <KeyInfo>Scheduled Date</KeyInfo> <Context>New Service Order</Context> <Explanation>Unable to perform the work within the required timeframe, alternate date: 2008-06-11</Explanation> </Event> </TransactionAcknowledgement> In summary, WA accepts the transaction with a new date provided instead of issuing a warning with a new date. | 2008-06-10 |  | Open | Low |  | Process the ERROR 1912 from the Accept in the same way for a WARNING 1912.
Delivered in CR#9 Part 2 on 24/12/2012 | Closed | 14 | Service Orders | Errors | Section 2.5.c suggests that the error issued should be "Retailer is not permitted to raise this service order type" (error 1945). WP currently Issue "Recipient is not responsible for the supplied NMI" (error 1923). To be fully compliant with NEM B2B, WP should change this to error 1945. | 2008-06-23 |  | Open | Low |  | WP believe that the end result of the process is likely to be the same, so this is a low priority fix.
Delivered in CR#9 Part 2 on 24/12/2012 | Closed | 15 | Service Orders | Errors | Clause 2.6.2a – states that "if a retrospective date is provided in the SO request the service provider will assume the schedule date is the date the request was received". In WA this will actually result in the transaction being TransNack'd. We need to change the WP processing. | 2008-06-23 |  | Open | Low |  | Always raise service orders with a scheduled date in the future (today will be accepted, although for most SOs this will be automatically changed to at least today+1 for SLA compliance. This will only be a problem if there is an extended outage on the gateways, which is unlikely (see related item #41).
| Open | 16 | Service Orders | Multiple Service Orders | Section 2.12.14.1 Describes the allowed combinations of service orders from the current and prospective retailer. The WA market should comply with the rules defined by the NEM, but extent of compliance to these rules will need to be tested in the WA market. The volume of scenarios where WP received service orders from two different retailers has been quite small to date in the WA market, although it is growing. | 2008-06-25 |  | Open | Low |  | The market might receive transaction rejections when they would normally expect the Network Operator to accept these transactions. If this occurs, please contact the Network Operator directly to resolve.
| Open | 17 | Standing Data | Meter Exchange | When there is a reading exception on the meter exchange, a full SDU is published with just the new meter, even though the partial SDUs that indicate the removal of the old meter have not yet been sent. | 2008-05-20 |  | Open | Low |  | On clearing of the related reading exception, the correct standing data is published. The end result is that the final FULL SDU represents the NMI details for the completed process.
| Open | 18 | Standing Data | De-Energise | When a de-energise is completed Western Power currently turn off the register, while in a NEM process, the register should be left turned on. This affects the SDU published to market. This can be corrected with a Configuration change in WP's systems but related readings publication issues need to be considered. These may impact on current franchise customer billing processes. This issue is also described in Defect 52 (Re-energise side). | 2008-05-20 | 2008-07-19 | Open | Medium |  | The removal of registers for a De-energised meter should be ignored. If the Meter is removed, the registers should also be removed. If a meter is reconfigured, the register removals should be used to adjust participant records.
| Open | 19 | Standing Data | Meter Exchange | This publishes a NMI status change showing Active from the Service Order field completion date. This is published as a redundant partial SDU. It is not required as the NMI is already active. If a Meter was de-energised, this change of NMI status is appropriate, but otherwise it is not required. | 2008-05-20 |  | Open | Low |  | Ignore the redundant change of NMI status from "A" to "A".
| Open | 20 | Standing Data | Remove Meter | Section 3.7.1: This process only issues a full SDU upon SO completion. There are no register or meter removal SDUs published. They should be published. | 2008-05-20 | 2008-07-19 | Open | Low |  | When a meter is no longer reported in the full SDU for a NMI, participants should also remove the related meter and registers. They should not wait for the remove meter and remove register partial SDUs.
| Open | 21 | Standing Data | NMI Merge process | Section 3.15.1: NMI Merge Process: Requires the Network Operator to send full SDU for all impacted NMI's to market. WP is not currently able to publish a full SDU for an Extinct (Status='X') NMI. The process of manually abolishing the old NMI should publish a partial SDU including the change to "Extinct " for the NMI. | 2008-05-20 | 2008-07-19 | Open | Low |  | An Email will be sent to participants notifying them of the NMI that has become Extinct. Participants should act on this email to correct their records.
| Open | 22 | Standing Data | Meter Reconfiguration | When the following Datastream attributes are changed, they are not published as Data stream changes in the partial SDU. They are only published against the Register in the Partial SDU. They are also published against the DataStream and Register in the Full SDU: - NMI suffix - Status The following Datastream attributes are published as required in a Partial SDU when they change: - Profile Name - Average Daily Load - Data Stream Type | 2008-05-28 |  | Open | Low |  | Changes to the Datastream NMI suffix and status should be determined from the FULL SDU only. Do not rely upon a partial SDU for changes to these standing data attributes.
n/a | Closed | 23 | Standing Data | Bulk Standing Data | This process is not defined in the WA Standing Data SID | 2008-05-30 | 2008-08-25 | Closed | Medium |  | Refer to version 2 of the SID and PD&G
n/a | Closed | 24 | Standing Data | NMI discovery Process | This process is not defined in the WA Standing Data SID | 2008-05-30 | 2008-08-25 | Closed | Medium |  | Refer to version 2 of the SID and PD&G
| Open | 25 | Standing Data | NMIStandingDataResponse | The MeterRequirementsForTransfer is not being provided to the non-current Retailer. This is needed to support transfer processing. | 2008-06-26 |  | Open | Low |  | Where required, participants should contact their account manager.
| Open | 26 | Standing Data | Roles | The RP is set incorrectly in the WA market. Should be set to Western Power or Horizon. NB: Also see defect 59 | 2008-06-26 |  | Open | Low |  | No market processes currently rely upon this data.
| Open | 27 | Technical Delivery Specifications | Message Format | Section 2.4 Message Format Point a1: WP does not currently support the delivery to market in a bundled form, but can accept bundled transactions. This was targeted for resolution with CR5, but now may be done separately. | 2008-06-17 |  | Open | Low |  | Participants should expect to receive one transaction per message, although they should attempt to comply with bundling of messages being sent to the Network Operator.
| Open | 28 | Technical Delivery Specifications | Transaction Model | Given WA is not using a multi-party to multi-party gateway like the NEM, WP needs to implement the equivalent check process across all inboxes and outboxes to perform the "flow control" process. While the process has not been implemented, if the "stop directories are defined, participants will be able to meet their obligations in relation to the required checks as defined under the B2B Tech Delivery spec. | 2008-06-20 |  | Open | Medium |  | Until implemented, there will be no automated check of the inbox sizes. Participants are reminded that they are obligated to process messages in the WA Gateway in a timely manner, as defined in the Build pack.
| Open | 29 | Technical Delivery Specifications | Transaction Model | WP processing does not comply with the MsgAck's defined on page 21 (step 4) and page 24 (step 5). This is related to the event codes used. | 2008-06-20 |  | Open | Low |  | Participants should avoid sending messages when: 1. Their mailbox has a very large backlog of messages 2. the header is invalid 3. the schema is invalid
| Open | 30 | Technical Delivery Specifications | Size | WP does not fully comply with the file size limit of 1MB uncompressed? The unzipped NEM12 files may be up to 1.3MB in the current system. The NEM13 files are not limited in size and are often between 3 and 4 MB. | 2008-06-22 | 2008-09-04 | Open | Low |  | Participants should plan to accept oversized NEM12 and NEM13 files.
| Open | 31 | Technical Delivery Specifications | Validation | WP does not fully comply with the ase:Event as described in 4.9.3. (pg 36) WP does not comply with 4.9.2.2 (pg 35) | 2008-06-22 |  | Open | Low |  | This events are unlikely to occur, and in a worst case scenario will be trapped by the absence of a TransactionAck.
Resolved via business process. DM#7901343 | Closed | 32 | Technical Delivery Specifications | Contingency Requirements | WP needs to develop the notification mechanism to be used in Outages. This is required as per sections 5.10.1 (3) and 5.10.2 a (2) and 5.10.3 a (2). | 2008-06-22 |  | Open | Low |  | There is a business process in place now that notifies impacted parties of outages. As part of the process, standardised email notifications are sent to Market Participants advising of system outages or issues that impact the Market, which includes updates, and notification when resolved.
| Open | 33 | Technical Delivery Specifications | Timing | 4.10 Timing: WP does not process transactions by priority, so will not comply with 60 min TransAck on “High Priority” transactions in 95% of cases. | 2008-06-22 |  | Open | Low |  | All service orders are processed as a high priority by Western Power, with TransNacks also sent as a high priority. TransAcks on the other hand may be delayed until end of day in worst case scenarios. If this does become an issue with the market, WP will escalate resolution.
| Open | 34 | Technical Guidelines | Address | WP does not support the LocationDescriptor. This will be needed to support the Change to rural addressing. NB: The XML does support this field. | 2008-06-16 |  | Open | Low |  | Not used in WA now, so minimal impact. Field is optional.
| Open | 35 | Standing Data | NMI | The checksum should be published in all Standing Data Messages, but this is currently absent from the partial SDU, and this defect has remained unresolved as it allows participants to easily identify the partial standing data transactions. This allows participants to use just the Full or partial messages as they see fit. | 2008-06-29 |  | Open | Low |  | No impact.
n/a | Closed | 36 | Service Orders | New Connection | The WA Document Reference number (Retailer Account number) is currently extracted from the FormReference field in the ServiceOrderRequest XML message. This should be extracted from the FormNumber field in the XML, and the FormReference should be populated with "New Conn Ref". 25/8: This defect was raised in error. The system is working as required. | 2008-06-30 | 2008-08-25 | Closed | Low |  | The WA market participants should continue to pass the ref# in the FormReference as described in the B2B Documents. This change will be made to the WA market at a later stage.
Delivered in CR#9 Part 2 on 24/12/2012 | Open | 37 | Service Orders | Business Acceptance | In Rejected Service Order requests the keyinfo field is populated with the Retailer Service Order ID as required by the NEM. But, in the case of a rejected cancellation service order request, WP currently publishes a heading and the value (for example "Retailer Ref No:MARC_084997_1"). This exceeds the 15 char length defined in Section 4.4. | 2008-06-30 |  | Open | Low |  | Participants should expect and handle the heading + value.
| Open | 38 | Standing Data | Street Type | CRSE defined in WA list (XLS on web site), but not allowed by the XSD. CRSE cannot be used in WA, otherwise XML publication will fail. | 2008-06-30 |  | Open | Low | Pending | Will be resolved shortly.
| Open | 39 | Standing Data | DataStream Type | Char(1) in NEMMCO, but defined to allow full string in WA XML. As part of CR5 WA should revert to the publication of "I", "N", "C", "P". | 2008-06-30 |  | Open | Low |  | Participants should continue to process the WA published values (eg <DataStreamType>Consumption</DataStreamType>)
| Open | 40 | Events and Codes |  | The Network Operator currently publishes error codes in the TransACK "Code" field, but place the description of the code in the Explanation. According to the NEM B2B build pack, the description currently in the explanation should be in the "DESCRIPTION" attribute of the "CODE" field. | 2008-07-02 |  | Open | Low |  | Participants should use the error code only. If they want a description, this should be extracted from the explanation field of the message.
Resolved via business process. DM#7901343 | Closed | 41 | Technical Delivery Specifications |  | Extended Outages (sometimes 12 hours) on the message handling processes within the Network Operator systems sometimes delays the delivery and collection of messages from the WA B2B Gateway. This may lead to non-compliance on the processing of transactions. | 2008-07-06 |  | Open | High | 2008-08-01 | The Network Operator will communicate with market participants when these outages arise. There is a business process in place now that notifies impacted parties of outages. As part of the process, standardised email notifications are sent to Market Participants advising of system outages or issues that impact the Market, which includes updates, and notification when resolved.
| Open | 42 | Technical Delivery Specifications | Contacts | Page 30 describes a B2B contact List. This list is published by the Network Operator on the Web site, but it needs to include the technical contact details as outlined on Page 30 for message delivery issue escalation. Review and update contact list if required. | 2008-06-20 |  | Open | Low |  | Contact Account Manager in the first instance if a technical contact is not known to the participant.
Delivered in CR#9 on 30/04/2012 | Closed | 43 | Standing Data | Meter Read Type | This does not differentiate between Optional Self reader and Mandatory Self reader meters. The Network Operator has agreed that support for the Franchise market requires this differentiation to be published to market participants. This will be done via a minor adjustment in the values published to market. | 2008-07-07 | 2008-07-07 | Open | Low |  | Continue to determine this from own records and via contact with the Network Operator where required.
| Open | 44 | Standing Data | Hazard | The MeterHazard field in the NEM Standing Data allows for 12 characters to describe the hazard. In WA we currently publish a code. This should be changed to publish a description (eg "Dog" instead of "BD") within the 12 characters allocated. | 2008-07-07 | 2008-07-07 | Open | Low |  | Used codified list as published in the codes and events to interpret.
| Open | 45 | Service Orders | MeterSerialNumber | Section 4.1 (pg 56): B2B Procedure indicates that the MeterSerialNumber can be repeated for multiple meters. This is not currently supported in the WA Market. WA only supports one meter being specified, and allows for multiple meters to be specified in the "SpecialComments". | 2008-07-08 | 2008-07-08 | Open | Low |  | WA supports one meter being specified, and allows for multiple meters to be specified in the "SpecialComments".
| Open | 46 | Service Orders | Request: ContactTelephoneNumber + RetailerContactTelephoneNumber | Section 4.1 (pg 61 and 61): B2B Procedure indicates that the ContactTelephoneNumbers (2 variations) may be repeated up to a maximum of three times. This is not currently supported in the WA Market. WA only supports one Telephone number in each of the two instances, and allows for additional details in to be specified in the "SpecialComments" if required. | 2008-07-08 | 2008-07-08 | Open | Low |  | WA supports one Telephone number in each of the two instances, and allows for additional details in to be specified in the "SpecialComments" if required.
| Open | 47 | Meter Data Process | Meter Data Verify | The Network Operator does not support MDV requests to the full extent of the NEM B2B process (4 alternatives). WA only supports requests at the Meter level (i.e. NMI + Meter# specified). WA does not currently support the following types of MDV: - NMI Level : NMI only specified - Datastream Level: NMI, Meter and Datastream specified - Site configuration: NMI and configuration are specified | 2008-07-14 | 2008-07-14 | Open | Low |  | Participants should only submit requests at the meter level (i.e. NMI + Meter# specified).
| Open | 48 | Meter Data Process | NEM13 | Business process issue: "E"stimated basic readings have been published to Synergy where "S"ubstitutes were expected. This problem has been tracked down to a new business process. The business process and system rules are being reviewed to stop estimates being published to market. | 2008-07-16 | 2008-08-25 | Fix in progress | Low | 2008-08-01 | Treat "E" readings with past reading dates as "S"ubstitutes. The readings published will be for the same value as that produced via a substitute process (i.e. same estimation method expected). The reading date on the estimate for basic readings will be at least 5 days after the Scheduled read date (i.e. standard estimation time).
| Open | 49 | Standing Data | Consumption Type (Act Acc Ind) | Char(1) in NEMMCO, but defined to allow full string in WA XML. As part of CR5 WA should revert to the publication of "A", "C". | 2008-07-17 | 2008-07-17 | Open | Low |  | Participants should continue to process the WA published values (e.g. <ConsumptionType>Cumulative</ConsumptionType>).
| Open | 50 | Standing Data | De-Energise | Section 3.4.1: As described in the Procedure, no partial SDU's are published in this process (i.e. current process is correctly documented). If the full SDU is stopped, then the partial SDU will need to be published in this scenario. | 2008-07-19 | 2008-07-19 | Open | Low |  | Participants should continue to use the full SDU to identify de-energised meters as well as using the service order response (for Retailer initiated de-energises).
| Open | 51 | Standing Data | De-Energise | Section 3.4.1: As described in the Procedure, WA allows for a single meter to be de-energised on a NMI. This is currently supported by a meterStatus of "D" in the WAeXML. With the CR5 alignment this status will be removed from the standing data. At this time, the process of notifying the market of individual meter de-energise will need to be reviewed. | 2008-07-19 | 2008-07-19 | Open | Low |  | Participants can use the partial SDU to identify de-energised meters on a NMI that has other energised meters.
| Open | 52 | Standing Data | Re-Energise | Section 3.5.1: As described in the Procedure, WA changes the register status from "R" to "C" as part of a re-energise, while the register status should stay as "C" during a period of de-energisation and therefore would not need to have a change published in a partial SDU as described in the procedure. This issue is also described in Defect 18 (De-energise side). | 2008-07-19 | 2008-07-19 | Open | Low |  | On the de-energise, the removal of registers for a De-energised meter should be ignored. If the Meter is removed, the registers should also be removed. If a meter is reconfigured, the register removals should be used to adjust participant records. This action on the de-ens means that these partials can be ignored if the register are already know to the retailer for the related meter.
| Open | 53 | Technical Guidelines | Address | Section 3.4: While the market participants are requested to comply with the procedure, the Network Operator does not fully utilise all provided details. This will be resolved as an internal WP defect. The details not fully used include: - PersonNameType - ServiceComment on Telephone numbers - ServiceType on Telephone numbers | 2008-07-19 | 2008-07-19 | Open | Low |  | No impact on Retailers.
| Open | 54 | Meter Data Process | Meter Data Notify | Section 4.3: The Network Operator does not publish the ParticipantRole as required by the B2B Procedure for MDN transactions. These transactions should include "The market role of the Participant to whom the data is being provided. Participant Role as published in MSATS." NB: This also affects the "Tech Build Pack" section 4.1.2.1 | 2008-07-20 | 2008-07-20 | Open | Low |  | Participants should assume that they are receiving the data because they are the FRMP.
| Open | 55 | Service Orders | Service Order Response | Section ?: The Network Operator does not publish the responseType="Closure" in the Service Order response. NB: This also affects the "Tech Build Pack" section 4.2.4. | 2008-07-23 | 2008-07-23 | Open | Low |  | "Closure" is the only valid value, so this should be assumed by the recipients.
| Open | 56 | Technical Specification | aseXML | As defined in the aseXML examples for WA, the XSD should be available on the Western Power Web site at: "http://www.westernpower.com.au/aseXML/schemas/r17/WA:r2.00/aseXML_r17_WA_r2.00.xsd" | 2008-07-29 | 2008-07-29 | Open | Low |  | The XSD is available in a zip file from http://www.westernpower.com.au/mainContent/workingWithPower/NetworkAccessServices/MeteringTransferCodes/Build_Pack.html
| Open | 57 | Service Orders | Service Order Response | Product Codes: the WA market does not support the following Product Codes: - "No Charge" - "TBA" - "As Quoted" WA currently issues a "0" product code instead of "No charge" in some cases. | 2008-08-05 | 2008-08-05 | Open | Low |  | Expect "0" instead of "No charge". "TBA" and "As quoted" will need to handled off-market.
| Open | 58 | Meter Data Process | Meter Data Notification | Participant Build Pack (section 4.1.2 pg 46 Line number 520) requires the following: "Where a ase:MeterDataNotification sent in response to an ase:MeterDataMissingNotification or ase:MeterDataVerifyRequest is not accepted via the ase:TransactionAcknowledgement (with a ase:@status of “Reject” or “Partial”) the MDP must ensure that any additional ase:MeterDataNotification sent to rectify the issue contains an ase:Transaction@initiatingTransactionID that corresponds to the ase:Transaction@transactionId value of the original Request." The Network Operator does not fully support this process. The handling of the resending is not supported through XML transactions. | 2008-08-05 | 2008-08-05 | Open | Low |  | Where the Network Operator receives a Partial or Reject for this transaction type, the remedial action will require the resubmission of another Meter Data History/Missing request, or the publication of the data in the next standard MDN. WP will not currently publish a second MDN for the one MDV.
| Open | 59 | Customer Transfer | Roles | The RP is incorrectly set in the WA market to the incoming Retailer as part of the CTR process (standard and erroneous transfer). The RP should not be changing as part of this process and should remain as the assigned Network Operator (Western Power for contestable market). The WA documentation includes the setting of the RP as a defined step in this process. When the system is corrected, the documentation should also be corrected (i.e. remove step and sample transactions from the WA procedure). NB: Also see defect 26. | 2008-08-05 |  | Open | Low |  | No market processes currently rely on this data.
| Open | 60 | Customer Transfer |  | section 4.1.1.1 (Paragraphs 1 & 2): This process needs to be reviewed to ensure that it reflects the full end-to-end CTR process, including: - Immediate issuance of a CTR response (assigning a Network Operator CTR ID). This is prior to the Transack, which needs to wait on manual review of the CTR. | 2008-08-15 |  | Open | Low |  | No market processes currently rely on this data.
| Open | 61 | Codes | Street Type | While the market standard street types allow for the following codes, they are not currently supported by the WA Network Operator: PSGE (Passage), RTRN (Return), WOOD (Wood) | 2008-08-25 |  | Open | Low |  | Do not use these street types.
| Open | 62 | Meter Data Process | Meter Data Notification | The NEM12 CSV data should be wrapped with a "<CSVIntervalData>", but in the WA market the NEM12 data is wrapped with "<CSVConsumptionData>". NB: The example in the participant build pack will also need to be updated when this is fixed. | 2008-09-04 |  | Open | Low |  | Expect both NEM12 and NEM13 to be published with <CSVConsumptionData>.
| Open | 63 | Standing Data | Bulk Standing Data | Two issues have been identified with the bulk Standing Data Extract: 1. The meter location is published as a code (LS) instead of the text description (Left Side). The XML standing data correctly publishes the description and not the code. 2. The route published includes the "(Downloaded)" text where the route is in fact downloaded for reading. This should only include the Route name. The XML standing data does not include this extra information. | 2008-09-30 |  | Open | Low |  | WP will provide the Meter Location translations on request.
| Open | 64 | Technical Delivery Specifications | WA XML Header | Messages published by the Network Operator include single quotes in the first line of the aseXML as shown below: <?xml version='1.0' encoding='UTF-8' ?> while it should include double quotes, as shown below: <?xml version="1.0" encoding="UTF-8" ?> NB: Participants should use double quotes for all messages. | 2009-02-06 | 2009-02-06 | Open | Low |  | Participants should process transactions with single quotes in the same way as transactions with double quotes
| Open | 65 | Standing Data | NMI Class | Messages published by the Network Operator include NMI Classifications of: "<5.7KW" ">5.7KW" When a character ">" is included in an xml message, it should be translated to "&gt;", but the current system is not doing this translation. This may affect any XML message, but is definitely an issue for the NMI Class in the SDU. NB: "<" is being translated as expected to "&lt;" and "&" is being translated to "&amp;". | 2009-02-06 | 2009-02-06 | Open | Low |  | Participants should process transactions with ">" instead of expecting the &gt;
Delivered in CR#11 on 24/12/2012 | Closed | 66 | Meter Data Process | Meter Data Notify | According to the AEMO document "Metering Data File Format Specification NEM12 & NEM13", the definition of the NMI Configuration is: "String of all NMISuffixes applicable to the NMI. The NMIConfiguration must represent the actual configuration of the site | 2012-09-06 | 2012-09-06 | Open | Medium | 2012-12-22 | Participant specific workarounds in place.
| Open | 67 | Meter Data Process | Meter Data Notify | Invalid NEM12 files during meter exchange - Duplicate 200 and 300 records sent to market. Where a meter is exchanged in the middle of the day, and all registers are the same before and after the exchange, the current NEM12 process will create two sets of | 2012-09-06 | 2012-09-06 | Open | Medium | 2012-12-22 | Participant specific workarounds in place.
| Open | 68 | Technical Delivery Specifications | Stopbox Functionality | The Network Operator has not implemented the Stopbox functionality as defined below: Section 4.12.1 MSATS B2B Handler Flow Control Management a. NEMMCO The Network Operator must ensure that the MSATS B2B Handler provides the following flow control management functionality. This functionality is a protection mechanism against file overloading of a Recipient s Outbox. b. NEMMCO The Network Operator must ensure that the MSATS B2B Handlers flow control management functionality is based on the use of flow control files. Two types of flow control files must be used. The first flow control file is named B2Bholdinp.stp and is located in the Recipient s Outbox. The second flow control file contains the name of the Recipient who is at the warning limit (ParticipantID_holdinp.stp) and must be located in a special directory stopbox located at the same level as Inbox and Outbox and repeated for each Participant.
Delivered in CR#15 on 11/12/2015 | Closed | 69 | Service Orders | New Connection | "OffPeakRequirements" Section 4.1 (pg65): B2B Procedure states that the "OffPeakRequirements" field as Required and Not Required. Section 4.2.3.8 (pg108): Participant Build Pack states the "OffPeakRequirements" as Optional, however Mandatory if the type of metering required known to the Retailer. The documents do not align, and the definition of the use of Mandatory vs Required is different in the documents. The behaviour needs to be determined and agreed with both documents aligned accordingly. Currently the Network Operator's system rejects any New Connection Service Orders where the Off Peak Requirements field is not provided. | [5 empty] | Participants to provide field in Service Order
Delivered in CR#15 on 11/12/2015 | Closed | 70 | Service Orders | New Connection | "InstallationType" Section 4.1 (pg64): B2B Procedure states that the "Installation Type" field as Required for the WA Market. Section 4.2.3.8 (pg107): Participant Build Pack states the "InstallationType" field is Optional, however Mandatory if the detail is known by the Retailer. Western Power has identified this as a clerical error, as it should have been Mandatory since inception. Currently the Network Operator's system rejects any New Connection Service Orders where the Installation Type field is not provided. | [5 empty] | Participants to provide field in Service Order
Delivered in CR#15 on 11/12/2015 | Closed | 71 | Service Orders | New Connection | Section 4.1 (pg61): B2B Procedure states the "ScheduledDate" field as Not Required for the WA Market. The Network Operator's system rejects any New Connection Service Orders where the Scheduled Date field is not provided. Note this field is referred to as the "Preferred Appointment Date" field in the Network Operator's system. Western Power has identified this as a clerical error, as it should have been Mandatory since inception | [5 empty] | Participants to provide field in Service Order
Delivered in CR#15 on 11/12/2015 | Closed | 72 | Service Orders | New Connection | Section 4.1 (pg55): B2B Procedure states that the "ServiceTime" field as Not Required for the WA Market. The Network Operator's system rejects any New Connection Service Orders where the Service Time field is not provided. Western Power has identified this as a clerical error, as it should have been Mandatory since inception | [5 empty] | Participants to provide field in Service Order
| Open | 73 | Technical Delivery Specification | Validation | WP does not fully comply with the ase:Message Acknowledgement as described in 4.9.3. (pg 36). In the event an invalid enumeration value is provided in the aseXML, the file will fail in the Metering Business System, however the Participant will not be notified via a message acknowledgement. | [5 empty] | An automated report can be provided to the Participants detailing the failed transactions and corresponding error messages, to an agreed email address.
| Open | 74 | Service Orders | All | WP rejects service order requests where the Business Name and associated contact details are provided, and the Customer Consultation Required field is set to True. The rejection reason provided is "CustomerDetail - No contact supplied". For other scenarios the messages are not rejected. | [5 empty] | Participants should set the Customer Consultation Required field to False where a Business Name is provided.